## Slide 1
American Bar Association
Forum on the Construction Industry
Fall Meeting – 2012
Construction Law Program for State and Local Government Attorneys and University Counsel:
Pulling Together for a Winning Strategy
Co-sponsored by the ABA Government and Public Sector Lawyers Division

## Slide 2
American Bar Association
Forum on the Construction Industry
Fall Meeting – 2012
Moderator:
John Buzz Tarlow
Bozeman, MT
Segment 1
Owner - Design Professional Considerations for Contracts and Project Delivery Methods
Kristine A. Kubes
Minneapolis, MN
Suzanne M. McSorley
Lawrenceville, NJ

## Slide 3: INITIAL PRINCIPLES
Communication – critical between parties
  Impacts:
    Change control
    Cost control
    Delay control
    Dispute control
  Guides for Good Communication:
    Partnering
    Big Room
    DRB

## Slide 4: INITIAL PRINCIPLES
Selecting Project Delivery Method
  Jurisdictional requirements/restrictions?
  Identify and address Owner’s main concerns
  Analyze advantages/risks of each method
  Main forms:
    Design – Bid – Construct
    Multi-Prime
    Construction Management – Agency
    Construction Management – At–Risk
    Design-Build

## Slide 5: INITIAL PRINCIPLES
Design – Bid – Construct
  Linear process
  One phase should be completed before the next
  Usually involves a fixed price
  Method traditionally used – familiarity
  Longer time-span from design to completion
  Less opportunity for value engineering

## Slide 6: INITIAL PRINCIPLES
Multi-Prime
  Owner contracts directly with multiple trades
  Cost-competitive
  Responsibility for coordination rests on Owner
  No single point of contact (can be problematic)

## Slide 7: INITIAL PRINCIPLES
Construction Management
  – Agency
    Think Multi-Prime plus one: the CM
    CM is consultant to Owner
    Opportunity for early consult on VE/constructability
  At-Risk
    Many pricing options for CM
    Opportunity for early consult on VE/constructability

## Slide 8: INITIAL PRINCIPLES
    Design-Build
  Single point of contact/control
  DB can be design-led or builder-led
  Owner cedes control to DB
  May lead to faster project delivery
  Heightened importance on communication from Owner to DB about design intention for project

## Slide 9: DESIGN ISSUES
Defining Project Scope
  “Programming Phase”
Defining Project Budget
  Owner’s responsibility/impact on budget
  Designer’s responsibility/impact on budget
  Budget ≠ Construction Estimate

## Slide 10: DESIGNER – OWNER ISSUES
Owner is key player in maintenance of schedule:
Communication responsibility
Timely decisions/selections
  Owner must abide by schedule, too
  Cost and time impact of late responses
Often area of misunderstanding, finger-pointing

## Slide 11: DESIGNER – OWNER ISSUES
Intellectual Property Issues
  “Instruments of Service”
  Form: How will instruments be used by:
    Design team
    Contractor
    Owner for facility use/maintenance
  Who retains rights to instruments at end of project?
  Contract issue
  Licenses for use, leaving rights intact

## Slide 12: DESIGNER – OWNER ISSUES
Building Information Modeling (BIM)
How is BIM used?
  Construction Model
  Operations Model
Financial implications
Control/Management implications
Liability: Who is liable design and/or tech?

## Slide 13: DESIGNER – OWNER ISSUES
Scope of designer’s authority during construction
For each contract/project, parties must:
Define “construction administration”
Define DP role and services during construction
Evaluate cost implications
Decide: Who resolves disputes?

## Slide 14: OWNER’S PROJECT CONTROLS
Level and frequency of reporting
Change management
  Requirements for pricing, documentation
Process for payment applications/review
Schedule updates
Contract needs to confirm terms
Owner/Contractor teams needs to be on-board and adhere to terms

## Slide 15: OWNER’S PROJECT MANAGEMENT ROLE
Effective Owner’s Representative
Critical to project success
Interacting with design and/or construction team throughout project
Define responsibilities and carry them out
Experience varies – may need help from a contracted CM

## Slide 16: OWNER - DESIGNER LIABILITY
Frequent issue during claims process:
Who is responsible for design – Owner or DP?
U.S. v. Spearin, 248 U.S. 132 (1918)
Owner warrants constructability of plans when Owner or its agent designer presents plans for construction
Contractor not liable for design issues

## Slide 17: Questions?
Kristine Kubes: kristine@kubeslaw.com
Suzanne McSorley: SMCS@stevenslee.com
Thank You…

## Slide 18
American Bar Association
Forum on the Construction Industry
Fall Meeting – 2012
CONSTRUCTION RISK ALLOCATION
Joel K. Gerber
Savannah, GA
Jack O’Neil
Breckenridge, CO
Aaron P. Silberman
San Francisco, CA
Segment 2
Moderator:
John Buzz Tarlow
Bozeman, MT

## Slide 19: Issues of Frequent Concern Arising Between Owner/Contractor
Constructability of plans
Differing site conditions
Price/cost escalation
Consequential damages
Performance and payment bonds
Defective work identified before completion

## Slide 20: Issues of Frequent Concern Arising Between Owner/Contractor
  Indemnity and Insurance
  Changes
  Scheduling & Delays
  Terminations
  Disputes

## Slide 21: Constructability of plans – U.S. v. Spearin, 248 U.S. 132 (1918)
Owner warrants constructability of plans when it or its agent designer presents plans for construction
Contractor not liable for design issues
Owner’s practical considerations

## Slide 22: Differing Site Conditions
What is a DSC?
Examples
  Generally
  In remedial construction
Types of DSC
  Type I
  Type II
  Example DSC clauses
  Qualification for remedial work

## Slide 23: Price/Cost Escalation
Price Escalation Clause (PEC) (material and labor)
  What is a PEC?
  Recent common examples
  Without a PEC, contractors’ potential legal alternatives to account for unforeseeable risks:
    Force majeure clause
    Impossibility of performance
    Mutual mistake
    Commercial impracticability
Federal government clauses
AIA standard fixed-price contract clause

## Slide 24: Consequential Damages
What are consequential damages?
Types of owner consequential damages
Types of contractor consequential damages
Waiver

## Slide 25: Performance and Payment Bonds
What is a performance bond?
What is a payment bond?
Are they required on government projects?
  Bond requirements on federal projects – the Miller Act
  States’ “Little Miller Acts”
Performance bond – surety’s options in the event of a default
  Tendering penal sum of bond
  Takeover and completion
  Tendering a new contractor
  Financing the surety’s principal
  Do nothing

## Slide 26: Performance and Payment Bonds
Payment bond claims
  For Miller Act bonds (federal):
    First and second tier subcontractors and suppliers are covered
    Lower tiers are not covered
    Notice of claim requirement
    Deadline for lawsuit foreclosing on bond
  Little Miller Act bonds may vary
  AIA bonds may vary

## Slide 27: Defective Work Identified Before Completion
Federal projects (Inspection of Construction clause)
  Timely notice of rejection requirement
  Reasonable cure period requirement
  Economic waste limitation
AIA clause re contractor obligation to correct non-conforming work

## Slide 28: Indemnity and Insurance
General issues
  State law limitations on indemnity
  Need for thorough treatment in contract
  Need to relate insurance & indemnity provisions to each other
Indemnity
  Personal injury
    To persons working on the project
    To visitors to the site or persons adjacent to the site
    To people occupying building during construction

## Slide 29: Indemnity and Insurance (Cont.)
  Property damage
    Property on or adjacent to the site
    Typically excludes damage to “the work” itself
  Violation of patent or other IP rights
  Safety violations at project site/regulatory liability
  Control as factor in indemnity in remedial construction on occupied, functioning structures
  Hazardous materials

## Slide 30: Indemnity and Insurance (Cont.)
Insurance
  Does insurance program required of contractor team provide the protection owner requires?
  Does it dovetail with the indemnity requirements?
  Does it require additional insured endorsements? Should it?
  Is the required insurance program commercially available?
  How can owner make sure all parties have required insurance in place before work commences?

## Slide 31: Indemnity and Insurance (Cont.)
  Typical insurance requirements
    Contractor:
      Commercial General Liability (CGL) and Umbrella/Excess Coverage
      Worker’s compensation and employer’s liability insurance
      Builder’s Risk
    Other contractor coverages to consider:
      Contractor’s professional liability
      Contractor’s pollution liability
      Property coverage for Contractor’s tools, etc.

## Slide 32: Indemnity and Insurance (Cont.)
  Architect:
    Professional liability/errors & omissions (E&O) coverage
    Additional coverages if architect is going to be doing any work at the project site
  Wrap-Up insurance programs: OCIPs, CCIPs

## Slide 33: Changes
Generally, contracts say:
  No verbal changes are allowed
  Contractor must continue to work in the event of a dispute
Despite these provisions, some jurisdictions allow contractor recovery for constructive changes, at least absent a government showing of prejudice

## Slide 34: Changes (Cont.)
Standard change order definitions
Bilateral change orders and construction change directives (CCD)
Equitable adjustments in price and time
Requirement that contractor continue to work in the event of a dispute regarding a change

## Slide 35: Scheduling and Delays
Standard clauses
Need to decide and define scheduling responsibilities
  Who is responsible for creating and maintaining the schedule? When must it be created and updated? What must it contain?
Special issues in scheduling for remedial projects

## Slide 36: Scheduling and Delays (Cont.)
Who caused the delay?
  Contractor
  Government
  Others (third parties, force majeure, etc.)
  Concurrent delay

## Slide 37: Scheduling and Delays (Cont.)
Contractor-caused delays to completion
  Government duty to notify
  Excusable delays
  Government remedies
    Contractor duty to accelerate
    Liquidated damages
    Actual damages
      Direct damages
      Consequential damages

## Slide 38: Scheduling and Delays (Cont.)
Government-caused delays to completion
  Contractor duty to notify
  Contractor remedies
    Time extension
    Contractor ability to accelerate (and recover)
    Damages
      “No damages for delay” clauses
        Allowed? Depends on jurisdiction
      Liquidated damages – not commonly used for contractor recovery for Government delays
      Actual damages
        Direct damages
        Overhead expenses
        Consequential damages

## Slide 39: Terminations
Termination for default
  Standard clauses
  Cure notice requirement
  Government damages/contractor recovery
  If the contractor contests the termination
  Strategic considerations

## Slide 40: Terminations (Cont.)
Termination for convenience
  Standard clauses
  Limits on ability to terminate for convenience
  Contractor recovery
    contract price for completed and accepted work
    costs incurred for work in progress plus a reasonable profit (or loss) on that work
    settlement expenses
    duty to limit post-termination costs vs. realities of shutting down a project

## Slide 41: Disputes
Contractor claims
  Administrative requirements
  Notice of claim
    Federal
      Requirement of written notice by contractor if claim is based on formal change in writing
      Notice requirements if claim is based on constructive change
      When/how notice requirements may be avoided
        Actual government knowledge
        Waiver
        Lack of prejudice to government
      Contract requirements (sample provisions)

## Slide 42: Disputes (Cont.)
  Court remedies
  Subcontractor pass-through claims
    Allowed? Depends on jurisdiction
    Severin doctrine
Government claims
  Backcharges and withholding retention
  Acceptance, effect of
Venue issues

## Slide 43: Questions?
Joel K. Gerber: Joel@rubnitzlaw.com
Jack O’Neil: JackO@WesternGroup.com
Aaron P. Silberman: asilberman@rjo.com

## Slide 44
American Bar Association
Forum on the Construction Industry
Fall Meeting – 2012
Segment 3
Project management: CONTROLS AND CLAIMS
Kurt Dettman Boston MA
Chuck Cobb
Boston MA
Moderator:
John Buzz Tarlow
Bozeman, MT

## Slide 45: STRUCTURING OWNER’S CONTROLS
Budget, schedule , quality and safety = the things you need to control
Owner’s lawyer must ensure reality based decision making and thoughtful risk allocation
Contract form determines what you need to focus on, watch out for
  Firm fixed price – owner need not audit cost
  Design Build – single point of responsibility to owner
  CM at Risk – GMP cost definitions, inclusions and exclusions matter

## Slide 46: PROJECT CONTROLS Planning
Preconstruction Planning is the best control
Clear fixed goals, broadly communicated
Fight over changes on the drawing board
Designers need to design to budget and schedule
Involve contractor as early as procurement laws allow

## Slide 47: PROJECT CONTROLS Information Flow = the goal
Accurate information must reach decision makers
Contract should require frequent reports
Clear the choke points, prevent information traps and filters
Human nature is against telling on yourself – require it anyway
Reports from Architect/CM to Owner’s Representative
Reports from Owner’s Representative to Owner

## Slide 48: PROJECT CONTROLS Systems
Jobsite website – transparent to Owner
Purchase and Delivery schedules updates
Weekly meeting minutes
  Tasks when assigned, when accomplished, ball in whose court for the next step?
  Follow up on old topics
  Look ahead

## Slide 49: PROJECT CONTROLS Monitoring Costs
Cost loaded schedule – contractors will try to front load costs
Yardstick to determine burn rate of costs vs. per cent complete
Monthly requisition – detailed backup to support cost claims
Contractor propensity to claim Changes may indicate a budget problem, an effort to recapture cost

## Slide 50: PROJECT CONTROLS Schedule Monitoring
Schedule devised by Contractor and accepted by Owner
Owners should plan to help contractors succeed
Project updates must be candid and realistic
Early schedule slips can doom a project timetable
Milestones matter

## Slide 51: PROJECT CONTROLS Claims Management
Early notice/duty to mitigate
Proper recordkeeping
Clear description of impact(s)
Substantiation
Entitlement to damages, extent of damages for audit trail (“connect the dots”)

## Slide 52: PROJECT CONTROLS Ensuring Quality
Risk of poor quality comes with a bid far below the next low bid
Risk of poor quality comes when general conditions are slashed to meet budgets
Superintendents exercise autocracy on the jobsite and must champion quality
Use lessons learned /continuous improvement vs. “blame game”

## Slide 53: PROJECT CONTROLS Safety
Nothing matters more
Not just the right thing to do – high risk that a serious injury will materially impact the work
Constructor safety management records should be monitored
Require prompt reporting of all injuries
Do root cause analysis

## Slide 54: PROJECT CLAIMS MANAGEMENT
Resolution vs. Prevention?
Crisis Management vs. Planning?
“Fitting the Form to the Fuss” ?

## Slide 55: Two Keys to a Successful Claims Management Program
Develop a Project Claim “Risk Profile”
Understand and Effectively Deploy:
  Dispute Avoidance Tools
  Dispute Resolution Tools

## Slide 56
Jury Trial
Bench Trial
Court Special Master
Court Settlement Conference
Arbitration
Mediation
Mini-Trial
Dispute Review Board
Joint Experts
Early Neutral Evaluation
Facilitation
Conciliation
Partnering
Structured Negotiations
Low Cost Resolution
High Cost Resolution
More Control
Less Control
ADR Continuum
Peer Review Panel
Dispute Review Board

## Slide 57: The Starting Point: Develop A Project Claim Risk Profile
Assess “Project Risk Profile” for Disputes and Claims
  Type
  Size
  Frequency
  Parties
  Impact on project

## Slide 58: Claims Avoidance Approaches
(Appropriate) Risk Allocation
Collaborative Project Management Principles
Incentives/Disincentives? Shared Risk/Reward?
Claims Avoidance Reviews
Early Notice/Mitigation Steps Required

## Slide 59: Managing Claims
“Real Time” Project Level Claims Management Approaches
  Step Negotiation Process
  Issue Resolution Ladder
  Senior Level Involvement As (And When) Needed

## Slide 60
Jury Trial
Bench Trial
Court Special Master
Court Settlement Conference
Arbitration
Mediation
Mini-Trial
Dispute Review Board
Joint Experts
Early Neutral Evaluation
Facilitation
Conciliation
Partnering
Structured Negotiations
Low Cost Resolution
High Cost Resolution
More Control
Less Control
ADR Continuum
Peer Review Panel
Dispute Review Board

## Slide 61: Claims Avoidance Tools: The “Green Zone”
Third Party Neutral Claim Avoidance Tools:
  Structured Negotiations
  Partnering
  Facilitation
  Dispute Review Board
  Conciliation

## Slide 62
Jury Trial
Bench Trial
Court Special Master
Court Settlement Conference
Arbitration
Mediation
Mini-Trial
Dispute Review Board
Joint Experts
Early Neutral Evaluation
Facilitation
Conciliation
Partnering
Structured Negotiations
Low Cost Resolution
High Cost Resolution
More Control
Less Control
ADR Continuum
Peer Review Panel
Dispute Review Board

## Slide 63: Claims Resolution Tools: “The Orange Zone”
Third Party Neutral Claim Resolution Tools:
  Early Neutral Evaluation
  Joint Experts
  Dispute Review Board
  Mediation
  Mini-trial

## Slide 64
Jury Trial
Bench Trial
Court Special Master
Court Settlement Conference
Arbitration
Mediation
Mini-Trial
Dispute Review Board
Joint Experts
Early Neutral Evaluation
Facilitation
Conciliation
Partnering
Structured Negotiations
Low Cost Resolution
High Cost Resolution
More Control
Less Control
ADR Continuum
Peer Review Panel
Dispute Review Board

## Slide 65: Claim Resolution Tools: “The Red Zone”
“Rolling the Dice” Claim Resolution Tools:
  Arbitration
  Court Special Master
  Court Settlement Conference
  Bench Trial
  Jury Trial

## Slide 66
Jury Trial
Bench Trial
Court Special Master
Court Settlement Conference
Arbitration
Mediation
Mini-Trial
Dispute Review Board
Joint Experts
Early Neutral Evaluation
Facilitation
Conciliation
Partnering
Structured Negotiations
Low Cost Resolution
High Cost Resolution
More Control
Less Control
ADR Continuum
Peer Review Panel
Dispute Review Board

## Slide 67
FIELD OFFICE LEVEL PARTNERING
SENIOR LEVEL PARTNERING
EXECUTIVE LEVEL PARTNERING
"FINAL DETERMINATION"
DISPUTE REVIEW BOARD
PROJECT DIRECTOR'S DECISION
LITIGATION/ ALJ
CLAIMS & CHANGES
ANALYSIS & NEGOTIATIONS
DISAGREE
AGREE
AGREE
AGREE
AGREE
AGREE
AGREE
AGREE
TIME UNTIL RESOLUTION
LEVEL OF RESOLUTION
AS TIME TO RESOLVE PROBLEM INCREASES, SO DO:
· WORK IMPACTS
· LEGAL EXPENSES
· APPEAL PREPARATION COSTS
· LIQUIDATED DAMAGES
· CUMULATIVE LOSSES
· NEGATIVE CASH FLOW
· ESCALATING HOSTILITY
ADVISORY DRB
Steps in Claim Resolution Process
Unresolved Issues Continue Through the Process to Agreement or Litigation
MEDIATION

## Slide 68: Thinking Outside The Box
Process Streamlining:
  Executive Steering Group for Negotiation Process
  Process “Chaperones”
  Joint Experts vs. Dueling Experts
  Early Mediator Involvement
  Information Exchanges vs. Discovery
  Expedited Arbitration Approaches

## Slide 69: Thinking Outside The Box
Collaboration is not a sign of weakness
Plan for the best, not the worst
Focus on interests , not positions

## Slide 70: Questions?
Kurt Dettman: kdettman@c-adr.com
Chuck Cobb: ccobb1223@gmail.com